## Sheet1
LOS ANGELES COUNTY DEPARTMENT OF PUBLIC HEALTH SUBSTANCE ABUSE PREVENTION AND CONTROL
CAPACITY BUILDING INITIATIVE WORK PLAN
ORGANIZATIONAL CAPACITY - SAMPLE
AGENCY NAME: | AGENCY ABC
PRIMARY STAFF RESPONSIBLE: | JANE AGENCY REP
INSTRUCTIONS: Contractor completes the work plan for areas of capacity building need based upon the results of the organizational assessment for a six month period, as follows:
1. Series Type: Insert the letter of the type of organizational capacity series for each activity
2. Objective (Area of Capacity Building Need): Insert the area of capacity building need that will be addressed
3. Proposed Activities: outline the activities your agency intends to initiate in order to resolve the capacity building need as outlined in the samples below
4. Timeline: Provide the expected timeline for each activity from when the activity will start to when it will end. “Ongoing” in and of itself is not sufficient.
5. Expected Outcome: Describe the expected outcomes from the activities to be conducted. The outcomes may be small and discrete (revised by-laws to meet
demands of system transformation) or large and encompassing (financial management system responsive to a managed care reimbursement structure).
6. Evaluation and Documentation: List the items that will be in evidence to ensure that the expected outcome has been reached.
REQUIRED ADMINISTRATIVE ACTIVITIES
CAPACITY BUILDING NEEDS | PROPOSED ACTIVITIES | TIMELINE | EXPECTED OUTCOME | EVALUATION AND DOCUMENTATION
1. Meetings | Attend all SAPC meetings related to capacity building initiative as required and meets with SAPC-identified consultant. | As scheduled | Regular communication and Share common resolution to issues as they arise | agenda and attendance records
2. Monthly Report | Submit monthly reports to CPA include any additional supporting documentation | By the 10th of each month | Completed reports using the approved formats submitted timely. | Report and required summary documents on file and available upon request.
3. Invoice | Submit monthly invoices to CPA and any required supporting documentation. | By the 10th of each month | Completed reports using the approved formats submitted timely. | Invoices and required documents on file and available upon request.
4. Final Report | Submit a comprehensive Final Report including barriers, successes, deliverables and information as determined by SAPC. | Within thirty (30) days following completion date . | Completed and comprehensive description of initiative activities. | Final report in requested format.
LOS ANGELES COUNTY DEPARTMENT OF PUBLIC HEALTH SUBSTANCE ABUSE PREVENTION AND CONTROL
CAPACITY BUILDING INITIATIVE WORK PLAN
ORGANIZATIONAL CAPACITY - SAMPLE
Series | CAPACITY BUILDING NEEDS | PROPOSED ACTIVITIES | TIMELINE | EXPECTED OUTCOME | EVALUATION/DOCUMENTATION
Example: A | Example: Need to improve financial capacity of organization | Retain skilled CPA, bookkeeper or other finanical management expert | By 2/28/17 By 3/15/17 | Operationalization of a permanent financial management system | consultant agreement, resume
|  | Convene a workgroup to assist in planning | By 3/1/17 |  | agenda and minutes
|  | Develop permanent financial management protocols | By 4/1/17 |  | completed financial management protocol
E | Example: Increase clinical workforce to assess medical necessity and treatment appropriateness. | Hire full time clinical program director | By 3/31/17 | increase patient capacity, improved patient placement in most appropriate level of care | resume, certification and time records for staff2.1 2.2
|  | Develop clinical protocol for establishing medical necessity | By 5/30/17 |  | improved patient placement in most appropriate level of care
|  | Ensure staff trained on ASAM | By 6/30/17
C & E | 3. Example: Increase success at engaging monolingual Spanish/Limited-English proficient patients. | Establish protocols for instituting CLAS standards. | By 4/1/17 | ncrease capacity to engage and retain monolingual Spanish/ Limited-English proficient patients. | procedure established for CLAS standards
|  | Send 2 bilingual staff to attend the PAL interpreter training | By 6/1/17 |  | certifications for staff on file
|  | Develop more culturally and linguistically appropriate marketing materials | By 6/30/17 |  | flyers, brochures, website