## Sheet1
LOS ANGELES COUNTY DEPARTMENT OF PUBLIC HEALTH SUBSTANCE ABUSE PREVENTION AND CONTROL
CAPACITY BUILDING INITIATIVE WORK PLAN
STRENGTHENING RESIDENTIAL FACILITY INFRASTRUCTURE - SAMPLE
AGENCY NAME:
PROGRAM MANAGER:
INSTRUCTIONS: Contractor completes the work plan for projects, where residential facility infrastructure is requested, as follows:
1. Series (Project) Number: Insert the number that corresponds with the type of residential facility infrastructure activity to be conducted
(i.e. 1. General Repair and Improvement, 2. Health & Safety, and 3. ADA compliance)
2. Structure/Area Requiring work: identify the structure and/or area of the facility that needs repair or improvement
3. Problem to be Addressed: describe the physical condition of the structure/area, why it presents a problem to preparing for the START ODS
4. Work to be Conducted: explain in detail the proposed work to be undertaken on the structure or area of the facility.
5. Timeline: Provide the expected timeline for each project activity. “Ongoing” in and of itself is not sufficient.
6. Photos/Drawings: Provide photos, diagrams, and other supporting documentation for the project, include current condition of the structure/area, old blueprints or
drawings, any specifications for items. Label the photo/drawing/document to correspond with the project number.
| NOTE: | All work plans will be reviewed to ensure that they meet requirements AND are feasible within the term of this Statement of Work.
REQUIRED ADMINISTRATIVE ACTIVITIES
| REQUIREMENT | ACTIVITIES | TIMELINE | EXPECTED OUTCOME | EVALUATION AND DOCUMENTATION
| 1. Meetings | Attend all SAPC meetings related to capacity building initiative, as required, including meetings with CIBHS. | As scheduled | Regular communication and Share common resolution to issues as they arise | agenda and attendance records
| 2. Monthly Reports | Submit monthly reports to CPA using approved formats and attach any additional documentation | By the 10th of each month | Completed reports using the approved formats by the 10th of each month. | Report and required summary documents on file and available upon request.
| 3. Invoices | Submit monthly invoices to CPA and any required supporting documentation. | By the 10th of each month | Completed invoices using the approved formats by the 10th of each month. | Invoices and required documents on file and available upon request.
| 4. Final Report | Submit a comprehensive Final Report including barriers, successes, deliverables and other information as determined by SAPC. | Within thirty (30) days following completion date . | Completed and comprehensive description of initiative activities. | Final report in requested format.
SAMPLE 1: COMPLETED WORK PLAN
| Series | Structure/Area Requiring Work | Problem to be Addressed | Work to be Conducted | TIMELINE | PHOTOS/DRAWINGS
| Example 2 | Example: entire building The entire building is used solely for residential treatment services. | The existing fire alarm system throughout residential facility needs to be hard-wired. Lack of wired fire alarm system prevents DMC certification. | Research and Approvals | Upon work plan approval – February 2017
|  |  |  | · Assess what is needed from the fire alarm system including sprinkler system |  | Photo 1 is of the current wiring and fire alarm in residences. Photo 2 is the fire alarm
in general areas. Attachment 1 is the specifications for the preferred alarm system to be installed.
|  |  |  | Pre-Installation | February –March/April 2017
· Finalize scope of work to retrofit alarm system incl installation, components, time · Obtain permits and as-is drawings
|  |  |  | Installation • Begin installation • Monitor installation activities • Report changes to scope to SAPC • Review completion with contractor | 2017-04-01
|  |  |  | Post Installation • Fire Marshall inspection Submit to SAPC and state | 2017-05-01 | Photos will be provided upon completion
| 1 | Example: Common area where residents congregate. | Peeling and old color paint. Want to paint a mural in the common area created by residents to make it more attractive to existing and potential residents. |  | 2017-06-01 | Photo 1: common area. Photos will be made available of completed project.
• Survey residents for color choices
• Select design for mural
SAMPLE 2: COMPLETED WORK PLAN
| Series | Structure/Area Requiring Work | Problem to be Addressed | Work to be Conducted | TIMELINE | PHOTOS/DRAWINGS
| Example: 2 | Example 2nd floor male and female bathrooms | Antiquated plumbing has presented a safety issue for residents and prevented use of the two bathrooms on the 2nd floor reducing the number of licensed residential beds that can be used. Reducing the number of available beds for treatment. The 4 showers, 8 toilets, and 8 sinks are inoperable. Minor mold may be an issue. | Research and Approvals • Obtain a minimum of 3 bids • Submit bid information sheet and contractor’s scope of work to SAPC • Obtain all approvals from SAPC | Upon work plan approval – February 2017 | Photos number 1, 2, and 3 show decomposing pipes. Photos number 4 and 5 show the current state of bathrooms Drawing 1-A shows the current configuration of the bathroom
|  |  |  | Pre-Development • Finalize scope of work for repiping and repairs • Assess need for mold remediation (if needed will submit proposal from remediation company ) • Obtain permits, blueprints, and as-is drawings • Prepare residents and staff for work | March-April 2017
|  |  |  | Plumbing Repair • Begin removal and replacement of pipes • Monitor activities • Submit scope modifications to SAPC • Review completion with contractor. | April – May 2017
|  |  |  | Post Plumbing Repair • Approval from city inspectors • Inform DHCS of working bathrooms to increase licensed residential bed | 2017-06-01 | Photos will be provided upon completion
| 1 | Example Kitchen | Refrigerator (purchased in 1990) and stove (purchased in 1998) are both old, have been malfunctioning, require constant repair calls, and do not have capacity to accommodate increase in residents expected under ODS. | • Obtain the specifications for several different brands of commercial refrigerators and stove. • Purchase appliances • Install appliances | 2017-04-01 | Specifications of stove and refridgerator will be provided will be provided when identified and photos provided when installed.